## Release SoP
WalkMe & Platform Release Cycle Standard Operating Procedure
| VERSION & OWNERSHIP |  |  |  | R - Responsible | Definition...
| LAST EDITED |  |  |  | A - Accountable
| EFFECTIVE DATE |  |  |  | C - Consulted
| OWNER |  |  |  | I - Informed
APPROVER
High-Level Standard Operating Procedure & RACI
|  | # | Stage | Description | IS/Product Team | WM Project Lead | WM Builder | Notes
|  | 1 | Recurring WM & Product SME | Recurring meeting between the content maintenance team & IS/Product to check in on the upcoming releases scheduled. If there is an upcoming release, team moves forward in the flow. Otherwise, this repeats. | R | R/A | C
|  | 2 | Change Management Meeting | Content maintenance team & IS/Product meeting to discuss the expected changes & timeline of the release. | R | R/A | C
|  | 3 | Release in Pre-Prod | The IS/Product team updates the content maintenance team when the new release is stable and available in a pre-production environment for WalkMe content testing. | R | A | C
|  | 4 | QA & Fix of WalkMe Content | Content maintenance team completes the standard QA & Fix process on WalkMe content, especially focusing on pages the IS/Product team noted changes on in the Change Management Meeting. |  | A | R
|  | 5 | Go-Live | Content maintenance & IS/Product team work together to coordinate the new release launch & WalkMe publish. | C | A | R
|  | 6 | Sanity Check | Sanity test of WalkMe content in the live environment & Insights review 1-3 days after go-live. |  | A | R

## Issue SoP
WalkMe Issue Standard Operating Procedure
VERSION & OWNERSHIP
LAST EDITED
EFFECTIVE DATE
OWNER
APPROVER
High-Level Standard Operating Procedure & RACI
|  | # | Stage | Description | End User | WM Project Lead | WM Builder | Notes
|  | 1 | Issue is sent to the WalkMe Team | End user submits the issue to the WalkMe Team via [insert communication/ticket system used to notify WM team, e.g. email domain, SNOW ticket, etc.] | R | R/A | C
|  | 2 | WalkMe Team prioritizes the issue against the backlog of requests | Issue is added to the project backlog for prioritization and resource assignment. |  | R/A | C
|  | 3 | QA & Fix of WalkMe Content | Content maintenance team completes the standard QA & Fix process on WalkMe content. |  | A | R
|  | 4 | Go-Live | Publish of content changes to production. |  | A | R
|  | 5 | Sanity Check | Sanity test of WalkMe content in the live environment & Insights review 1-3 days after go-live. |  | A | R